Force field analysis of the implementation of PM&E

| Positive forces | Score | Implementing PM&E | Negative forces | Score |
| --- | --- | --- | --- | --- |

Total

SWOT Analysis

Can also be useful depending on the data availability and the context of the exercise

Identifying Stakeholders

PADC Case in Cameroon: Stakeholder Map

| High Power | National Coordinator Traditional Authorities Elites | IFAD Supervisors Local Government Provincial Supervisor Other projects |
| --- | --- | --- |
| Low Power |  | M&E Focal Point Service providers Beneficiaries |
|  | Low Interest | High Interest |

Prepare for actions to move from the baseline situation (relative influence and interest of the various stakeholders) to more desirable one with respect the envisioned PM&E system

| Stakeholders | Nature of power or influence | Nature of interest (+ or -) | Actions needed to change the situation and make it useful for the PM&E system |
| --- | --- | --- | --- |
| A B C D E | Financial Social Political Religious Etc. | Improve power over a process Improve political profile Increase performance |  |

Defining Expectations & Objectives (of the PM&E system)

Is the focus on:

- Learning

- Strengthening the organization

- Resource allocation,

- Or, Service delivery

Stakeholder identification & Analysis:

- List “potential” stakeholders

- Analyzing power/influence of stakeholders (power/interties matrix)

- Identify gaps and corresponding actions to improve the power/interest of stakeholders as depicted on the map

- Conduct focus groups with key stakeholders to define objectives and/or expectations

- Organize face-to-face consultation with all stakeholders to confirm objectives

- Define final objectives of the PM&E system